## Sheet1
Years of Implementation
ID | Resource or Area | Project Title (status, if applicable) | Plan issue/goal addresses | Project description/need | Potential Partners | Planning Level Cost | Year by Year Cost Check (should = H) | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035
1 | Medicine Lake | Projects resulting from Medicine Lake TMDL Assessment | Impaired Waters: Medicine Lake delisting for nutrients | Projects and BMPs will vary depending on assessment results | Plymouth, Medicine Lake, TRPD | 2000000 | 2000000 | Years of Implementation 2028: 1000000; Years of Implementation 2029: 1000000
2 | Medicine Lake | Medicine Lake Shoreland Restoration (ML-14) (included in 2015 watershed plan but not implemented) | Lakeshore Erosion: Increase percentage of properties with native buffers on nutrient impaired lakes. | (This project may be redundant to #21 below and/or may be captured in Medicine Lake TMDL assessment recommendations from #1 above.) | Plymouth, Medicine Lake, TRPD | 150000 | 150000 | Years of Implementation 2032: 50000; Years of Implementation 2033: 50000; Years of Implementation 2034: 50000
3 | Northwood Lake | Projects resulting from Northwood Lake TMDL and Subwatershed Analysis (SWA) | Impaired Waters: Northwood Lake WQ improvements | Projects and BMPs will vary depending on assessment results | New Hope | 1000000 | 1000000 | Years of Implementation 2029: 500000; Years of Implementation 2030: 500000
4 | Lost Lake | Projects resulting from Lost Lake TMDL and Subwatershed Analysis (SWA) | Impaired Waters: Lost Lake WQ improvements | Projects and BMPs will vary depending on assessment results | Plymouth | 750000 | 750000 | Years of Implementation 2028: 500000; Years of Implementation 2029: 250000
5 | Crane Lake | Crane Lake Chloride Reduction Demonstration Project | Impaired Waters: Maintain or improve water quality in priority lakes and streams | Monitoring indicates that high chloride levels are likely impacting aquatic life. This project will study and implement practices to reduce chlorides reaching the lake, and could be a demonstration for implementation in other areas. | Minnetonka | 300000 | 300000 | Years of Implementation 2027: 300000
6 | Crane Lake | Retention of impervious area drainage at Ridgedale area (CL-3) (included in 2015 watershed plan but not implemented) | Impaired Waters: Maintain or improve water quality in priority lakes and streams | Crane Lake outlets to Medicine Lake; Examples of projects include bioswales, tree trenches, rain gardens | Minnetonka | 300000 | 300000 | Years of Implementation 2033: 300000
7 | Main Stem Bassett Creek | Bassett Creek Main Stem Restoration - Regent Ave to Golden Valley Rd | Impaired Waters: Achieve stable streambanks along all priority streams; Maintain or improve macroinvertebrate indices of biological integrity (MIBI) in priority streams; Maintain or improve water quality in priority streams | Will reduce phosphorus and sediment loading to downstream resources including Bassett Creek and Mississippi River. May possibly improve riparian and in-stream habitats. | City of Golden Valley | 2241000 |  | Years of Implementation 2026: 653500
8 | Main Stem Bassett Creek | Medicine Lake Road and Winnetka Avenue Long Term Flood Mitigation Plan Implementation - DeCola Pond F Flood Storage & Diversion Project | Flooding/Climate Change Impacts: Reduce flood risk to structures and infrastructures | Based on projects identified in the Medicine Lake Rd. and Winnetka Ave. Long Term Flood Mitigation Plan. Two projects already constructed (DeCola Ponds B&C and SEA School & Wildwood Park Projects). | Golden Valley, New Hope, Crystal | 4000000 | 4000000 | Years of Implementation 2027: 1000000; Years of Implementation 2028: 1000000; Years of Implementation 2030: 1000000; Years of Implementation 2031: 1000000
9 | Main Stem Bassett Creek | Bassett Creek Valley floodplain reduction and stormwater management projects | Bassett Creek Valley: Collaborate on evaluation, sequencing, and implementation of multi-beneficial projects within the Bassett Creek Valley to create regional flood storage, reduce floodplain by at least 8 acres, improve regional stormwater management, and improve creek access. | Projects that result in regional flood storage, reduce floodplain by at least 8 acres, improve regional stormwater management, and improve creek access. | Minneapolis, MPRB, Hennepin County | 5000000 | 5000000 | Years of Implementation 2031: 1000000; Years of Implementation 2032: 1000000; Years of Implementation 2033: 1000000; Years of Implementation 2034: 1000000; Years of Implementation 2035: 1000000
10 | Main Stem Bassett Creek | Restoration and stabilization of historic Bassett Cr channel north of Hwy 55, Minneapolis (included in 2015 watershed plan but not implemented) | Impaired Waters: Maintain or improve water quality in priority streams | Will reduce phosphorus and sediment loading to downstream resources including Bassett Creek and Mississippi River. Removed from CIP list due to low priority | Minneapolis | 1200000 | 1200000 | Years of Implementation 2033: 600000; Years of Implementation 2034: 600000
11 | Main Stem Bassett Creek | Bassett Creek Park water quality improvements or wetland restoration, Minneapolis (included in 2018 version of CIP list but later removed due to low priority) | Wetland Health & Restoration: Restore or enhance priority wetlands as opportunities arise or adjacent CIP projects are planned | Construction of BMPs benefitting Bassett Creek, potentially in conjunction with MPRB park renovations. May be an opportunity for a wetland restoration on the south side of Bassett Creek. Provides a better neighborhood connection to the creek. | Minneapolis, MPRB | 700000 | 700000 | Years of Implementation 2028: 350000; Years of Implementation 2029: 350000
12 | Main Stem Bassett Creek | Double Box Culvert Repair (FCP-1) (slated for 2026/2027) | Flooding/Climate Change Impacts: Reduce flood risk to structures and infrastructures | Maintenance of Flood Control Project; project would address needed repairs along the 5,600-foot-long tunnel | Minneapolis | 1200000 | 1200000 | Years of Implementation 2026: 850000; Years of Implementation 2027: 350000
13 | Main Stem Bassett Creek | Toledo Ave/Minnaqua Pond Stormwater Improvements & Flood Reduction (BC-13) – (slated for 2028/2029) | Impaired Waters: Maintain or improve water quality in priority lakes and streams; Flooding/Climate Change Impacts: Reduce flood risk to structures and infrastructures | Relocating infrastructure, creating flood storage, and redesigning the pond/stream interface will lower flood risk and damage, improve water quality of Bassett Creek and downstream waters, improve maintenance, and enhance vegetation and wildlife habitat. | Golden Valley | 900000 | 900000 | Years of Implementation 2028: 400000; Years of Implementation 2029: 500000
14 | Main Stem Bassett Creek | Bassett Creek Lagoon Dredging in Theodore Wirth Park (BC-7) | Impaired Waters: Maintain or improve water quality in priority streams; improve habitats for macroinvertebrates and fish | Original project was not completed to specifications. This project will finish the project and/or complete a project with similar outcomes in upstream areas. | Golden Valley, MPRB | 800000 | 800000 | Years of Implementation 2027: 400000; Years of Implementation 2028: 400000
15 | Main Stem Bassett Creek | Deep Tunnel Sediment Removal | Flooding/Climate Change Impacts: Reduce flood risk to structures and infrastructures | Maintenance of Flood Control Project; sediment removal near the outfall to the Mississippi River in conjunction with 2030 scheduled deep tunnel inspection. | Minneapolis, USACE | 2000000 | 2000000 | Years of Implementation 2030: 1000000; Years of Implementation 2031: 1000000
16 | Main Stem Bassett Creek | Deep Tunnel repairs | Flooding/Climate Change Impacts: Reduce flood risk to structures and infrastructures | Maintenance of Flood Control Project; perform repairs identified in tunnel inspection reports, including void filling, infiltration repairs, concrete debris removal, and shaft modifications, plus any additional repairs identified in the 2030 inspection. | Minneapolis, USACE | 5000000 |  | Years of Implementation 2035: 5000000
17 | Main Stem Bassett Creek | Bassett Creek restoration within Brookview Golf Course | Impaired Waters: Achieve stable streambanks along all priority streams; Maintain or improve macroinvertebrate indices of biological integrity (MIBI) in priority streams; Maintain or improve water quality in priority streams | From Golden Valley staff | Golden Valley | 2500000 | 2500000 | Years of Implementation 2030: 1250000; Years of Implementation 2031: 1250000
18 | Main Stem Bassett Creek | City Hall Campus Redesign Stormwater Improvements & Interpretive Area | Impaired Waters: Maintain or improve water quality in priority streams; potentially address chloride water quality goals and engagement goals | From Golden Valley staff; could be an opportunity to do something like MWMO plus Indigenous installation/reflection/vegetation, community gathering space, etc | Golden Valley | 750000 |  | Years of Implementation 2032: 750000
19 | Main Stem Bassett Creek | Stormwater & Habitat Improvements in Hampshire Park (includes flood mitigation) | Impaired Waters: Maintain or improve water quality in priority streams; Flooding/Climate Change Impacts: Reduce flood risk to structures and infrastructures | From Golden Valley staff | Golden Valley | 2500000 | 2500000 | Years of Implementation 2034: 1250000; Years of Implementation 2035: 1250000
20 | Main Stem Bassett Creek | Stormwater & Habitat Improvements in Orkla Park (includes flood mitigation) | Impaired Waters: Maintain or improve water quality in priority streams; Flooding/Climate Change Impacts: Reduce flood risk to structures and infrastructures | From Golden Valley staff | Golden Valley | 2000000 | 2000000 | Years of Implementation 2032: 1000000; Years of Implementation 2033: 1000000
21 | North Branch Bassett Creek | Bassett Creek Park Pond Dredging and Upstream Channel Improvements, Crystal | Impaired Waters: Maintain or improve water quality in priority streams | This project was originally studied in 2017 in conjunction with a study of Winnetka Pond dredging. The final project resulted only in dredging of Winnetka Pond with an understanding the Bassett Creek Park Pond dredging would be completed in the future. | Crystal | 1200000 | 1200000 | Years of Implementation 2030: 600000; Years of Implementation 2031: 600000
22 | Plymouth Creek | Plymouth Creek Restoration Project Dunkirk Lane to Plymouth Ice Center | Impaired Waters: Achieve stable streambanks along all priority streams; Maintain or improve macroinvertebrate indices of biological integrity (MIBI) in priority streams; Maintain or improve water quality in priority streams | Will reduce phosphorus and sediment loading to downstream resources including Medicine Lake. May possibly improve riparian and in-stream habitats. | Plymouth | 2600000 |  | Years of Implementation 2026: 1300000
23 | Plymouth Creek | Fernbrook Regional Stormwater Improvements | Impaired Waters: Maintain or improve water quality in priority streams; Flooding/Climate Change Impacts: Reduce flood risk to structures and infrastructures | This project in the city of Plymouth will construct a regional stormwater treatment system to reduce flooding and improve water quality in downstream Plymouth Creek and Medicine Lake in the area north of Highway 55 on Fernbrook Lane. | Plymouth | 3000000 | 3000000 | Years of Implementation 2027: 500000; Years of Implementation 2028: 500000; Years of Implementation 2029: 2000000
24 | Sweeney Branch Bassett Creek | Culvert Repair/Replacement: Sweeney Lake to Sweeney Branch Bassett Creek, Golden Valley | Flooding/Climate Change Impacts: Reduce flood risk to structures and infrastructures | This project in Golden Valley will repair or replace aging infrastructure that facilitates the flow of the Sweeney Lake Branch of Bassett Creek, helps to protect critical regional watermain infrastructure, and prevents flooding of nearby buildings and property. | Golden Valley | 1000000 | 1000000 | Years of Implementation 2032: 500000; Years of Implementation 2033: 500000
25 | Watershed-wide | Projects resulting from subwatershed assessments in prioritized areas | Multiple issues and goals in Watershed and Waterbody Quality category and Climate Resiliency and Flooding category | In addition to the planned subwatershed assessments (SWAs) for Nothwood Lake (#3) and Lost Lake (#4), and the Medicine Lake TMDL Assessment (#1), additional SWAs are planned in other areas of the watershed. SWAs will identify, target, and prioritize activities to improve conditions, including CIP projects. |  |  |  | Years of Implementation 2030: 100000; Years of Implementation 2032: 100000; Years of Implementation 2034: 100000
26 | Watershed-wide | Shoreline improvement projects on priority lakes | Lakeshore Erosion: Increase percentage of properties with native buffers on nutrient impaired lakes. | As identified by assessments or as be cost share program | Cities | 500000 | 450000 |  | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000
27 | Watershed-wide | Streambank restoration and channel/habitat improvements on priority streams; various segments | Impaired Waters: Achieve stable streambanks along all priority streams; Maintain or improve macroinvertebrate indices of biological integrity (MIBI) in priority streams; Maintain or improve water quality in priority streams | Based on surveys of streambanks and riparian areas; projects to restore streams, introduce in-channel habitat, overhanging vegetation, and woody debris | Cities | 2400000 | 2400000 | Years of Implementation 2031: 600000; Years of Implementation 2032: 600000; Years of Implementation 2034: 600000; Years of Implementation 2035: 600000
28 | Watershed-wide | Curly-leaf pondweed control for WQ improvement | Impaired Waters: Improve lake water quality AIS: Mitigate the impact of existing AIS infestations | Per AIS management policies. | Cities, Hennepin County, TRPD, MDNR | 200000 | 200000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000
29 | Watershed-wide | Implementation of recommendations from Street Sweeping Prioritization Project | Impaired Waters: Improve lake and stream water quality; reduce chloride loading to lakes and streams; reduce chloride concentrations in Bassett Creek by 10% | Potentially includes equipment purchase cost share or augmented street sweeping programs. | Cities | 400000 | 400000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000
30 | Watershed-wide | Private Developer Cost-share for Project Performance Beyond Minimum Standards (water quality and/or flood control) | Multiple goals including water quality improvements and flood reduction | Requested on multiple occasions by TAC. Fewer and fewer opportunities for projects on public land. Cooperation with private property owners is needed. | Cities | 900000 | 900000 |  | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000
31 | Watershed-wide | Chloride Reduction Projects or cost-share program | Impaired Waters: Reduce chloride loading to lakes and streams | Prioritization given to areas tributary to chloride-impaired waters. Cost share program could be developed for city and private entities. Examples include equipment upgrades, brining equipment, porous pavement, heated surfaces, reconfiguring sites for less ice build-up | Cities | 450000 | 450000 |  | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000
32 | Watershed-wide | Flood risk reduction cost share program (for habitable structures) | Flooding/Climate Change Impacts: Reduce flood risk to structures and infrastructures | Floodproofing or flood risk reduction projects for homes | Cities | 400000 | 400000 |  |  | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000
33 | Watershed-wide | Implementation of water quality improvement projects resulting from the Upper Mississippi River Bacteria TMDL (WS-1) (included in 2015 watershed plan but not implemented) | Impaired Waters: Reduce sources of bacteria to priority streams | Goose management, pet waste management projects, reduction of bacteria loading from ponds and pipes | Cities, MPCA | 100000 | 100000 | Years of Implementation 2030: 50000; Years of Implementation 2031: 50000
34 | Watershed-wide | CIP Project Maintenance | Multiple goals across all areas | Maintenance of past CIP projects | Cities | 450000 | 450000 |  | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000
35 | Wirth Lake | Wirth Lake Aeration | Impaired Waters: Maintain or improve water quality in priority lakes and streams; and Maintain or improve fish index of biologic integrity for applicable priority lakes | Implement results of Wirth Lake Aeration Study | MPRB | 150000 |  | Years of Implementation 2027: 150000
[6 empty] | 49041000 | 38250000 | 2863500 | 3010000 | 4510000 | 4960000 | 4860000 | 5860000 | 4360000 | 3810000 | 3960000 | 8210000
Note on G5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: $100k in 2023 CIP amendment
Note on G8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CL-4 has $300k in 2024-2028 CIP; are these the same project?
Note on G9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CL-4 has $300k in 2024-2028 CIP; are these the same project?
Note on G10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total cost includes $300,000 of funding from Golden Valley
Note on G11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Based on 2025-2029 draft CIP
Note on G12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Just a guess for now
Note on G13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Based on approx. average of creek projects in 2023 CIP amendment plus 20%
Note on G14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No estimate available, this is just a placeholder value
Note on G15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Based on Feb 2025 memo from Jim Herbert and 2025-2029 draft CIP
Note on G16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Based on 2025-2029 draft CIP
Note on G17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Based on 2025-2029 draft CIP
Note on G18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Need feasibility study to refine costs
Note on G19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Need feasibility study to refine costs
Note on G20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Based on approx. average of creek projects in 2023 CIP amendment plus 20%
Note on G24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: $1.0M in 2023 CIP amendment
Note on G25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Total project cost
Note on G26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Based on 2025-2029 draft CIP
Note on G27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Can’t find an estimate for this one
Note on G30: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Assumes 2 projects TBD over 10 years
Note on I10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3rd and final year of levies
Note on I25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2nd of two levies
Note on M18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Assumes project is implemented when the next 10-year inspection is due (2030).
Note on R19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Exact year will depend on 2030 inspection results. Could potentially wait until 2040 inspection year to perform this work.